## Cover
TEST REPORT DOCUMENT
Project Name | He thong Quan ly Su kien & Ho tro AI |  |  | Creator | Tran Xuan Thuan
Project Code | UEMS |  |  | Issue Date | 2026-07-11
Document Code | UEMS_XXX_vx.x |  |  | Version | 1.0
2026-06-20 | 1.0 | Khuu Xuan Nhan | A | - Create new test report. - Add Authentication test cases | None
2026-06-28 | 1.1 | Khuu Xuan Nhan | A | - Add Event Management test cases | None
2026-07-05 | 1.2 | Khuu Xuan Nhan | A | - Add Registration & Ticketing, Check-in & QR | None
2026-07-11 | 1.3 | Tran Xuan Thuan | M | - Review & update expected results | None
Note on D10: *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | He thong Quan ly Su kien & Ho tro AI
Project Code |  | UEMS
Test Environment Setup Description |  | 1. Server: Node.js/Express 2. Database: MongoDB 3. Web Browser: Chrome, Edge 4. Mang LAN/Internet
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Authentication | Authentication | Dang ky, Dang nhap, SSO, Quen/Dat lai mat khau | None
2 | Event Management | Event Management | Tao, de xuat, xet duyet, publish, tim kiem su kien | None
3 | Registration & Ticketing | Registration & Ticketing | Dang ky/huy tham gia, mua ve, thanh toan online | None
4 | Check-in & QR | Check-in & QR | Tao QR diem danh, quet check-in, thong ke tham gia | None
5 | Function E | Feature2

## Test Statistics
TEST STATISTICS
Project Name | He thong Quan ly Su kien & Ho tro AI |  | Creator |  |  | Tran Xuan Thuan
Project Code | UEMS |  | Reviewer/Approver |  |  | Khuu Xuan Nhan
Document Code | UEMS_XXX_vx.x |  | Issue Date |  |  | 2026-07-11
Notes | Authentication, Event Management, Registration & Ticketing, Check-in & QR
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Authentication | 9 | 0 | 0 | 0 | 11
2 | Event Management | 8 | 0 | 0 | 0 | 10
3 | Registration & Ticketing | 7 | 0 | 0 | 0 | 8
4 | Check-in & QR | 5 | 0 | 0 | 0 | 6
| Sub total | 29 | 0 | 0 | 0 | 35
| Test coverage |  | 82.8571 | %
| Test successful coverage |  | 82.8571 | %

## Authentication
Feature | Authentication | [13 empty] | Passed
Test requirement | Kiem thu chuc nang dang ky, dang nhap, dang nhap SSO va quen/dat lai mat khau cua he thong UEMS. | [13 empty] | Failed
Number of TCs | 11 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 9 | 0 | 0 | 0
Round 2 | 9 | 0 | 0 | 0
Round 3 | 9 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Register
AUTH-REG-01 | Dang ky tai khoan Guest hop le | 1. Mo trang Signup 2. Nhap ho ten, email, SDT, mat khau hop le 3. Nhan Dang ky | Tao tai khoan thanh cong, gui email/OTP xac thuc, chuyen ve trang dang nhap | None | Passed | 2026-06-02 | NhanKX | Passed | 2026-06-24 | NhanKX | Passed | 2026-06-24 | LinhNN
AUTH-REG-02 | Dang ky voi email da ton tai | 1. Mo trang Signup 2. Nhap email da dang ky truoc do 3. Nhan Dang ky | Hien thi loi "Email da duoc su dung", khong tao tai khoan | Da co tai khoan email nay | Passed | 2026-06-04 | LinhNN | Passed | 2026-06-26 | LinhNN | Passed | 2026-06-26 | TuanDPH
AUTH-REG-03 | Dang ky voi mat khau yeu / khong khop | 1. Nhap mat khau < 8 ky tu hoac confirm khong khop 2. Nhan Dang ky | Hien thi thong bao rang buoc mat khau, chan submit | None | Passed | 2026-06-08 | TuanDPH | Passed | 2026-06-29 | TuanDPH | Passed | 2026-06-29 | NhanKX
Login
AUTH-LOG-01 | Dang nhap voi tai khoan hop le | 1. Mo trang Login 2. Nhap email + mat khau dung 3. Nhan Dang nhap | Dang nhap thanh cong, tra ve JWT, chuyen ve trang chu theo role | Tai khoan da active | Passed | 2026-06-10 | NhanKX | Passed | 2026-07-01 | NhanKX | Passed | 2026-07-01 | LinhNN
AUTH-LOG-02 | Dang nhap sai mat khau | 1. Nhap email dung, mat khau sai 2. Nhan Dang nhap | Hien thi "Email hoac mat khau khong dung", khong cap token | None | Passed | 2026-06-12 | LinhNN | Passed | 2026-07-03 | LinhNN | Passed | 2026-07-03 | TuanDPH
AUTH-LOG-03 | Dang nhap tai khoan bi khoa | 1. Nhap thong tin tai khoan da bi Admin khoa 2. Nhan Dang nhap | Hien thi thong bao tai khoan bi khoa, tu choi dang nhap | Tai khoan bi khoa | Passed | 2026-06-15 | TuanDPH | Passed | 2026-07-06 | TuanDPH | Passed | 2026-07-06 | NhanKX
AUTH-LOG-04 | Dang nhap SSO bang email truong (Google) | 1. Nhan "Dang nhap voi Google" 2. Chon tai khoan email @fpt.edu.vn | Xac thuc Google thanh cong, tu dong tao/gan role Student, vao trang chu | None | Passed | 2026-06-17 | NhanKX | Passed | 2026-07-08 | NhanKX | Passed | 2026-07-08 | LinhNN
Forgot Password
AUTH-FGP-01 | Gui yeu cau quen mat khau | 1. Mo Forgot Password 2. Nhap email hop le 3. Nhan Gui | Gui email chua link/OTP dat lai mat khau | Email ton tai | Passed | 2026-06-19 | LinhNN | Passed | 2026-07-10 | LinhNN | Passed | 2026-07-10 | TuanDPH
AUTH-FGP-02 | Dat lai mat khau bang token het han | 1. Mo link reset da het han 2. Nhap mat khau moi | Hien thi loi token khong hop le/het han | Token da het han | Passed | 2026-06-02 | TuanDPH | Failed | 2026-06-24 | TuanDPH | Failed | 2026-06-24 | NhanKX
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Event Management
Feature | Event Management | [13 empty] | Passed
Test requirement | Kiem thu luong tao, de xuat, xet duyet (ICPDP), publish (CTSV) va tim kiem su kien. | [13 empty] | Failed
Number of TCs | 10 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 8 | 0 | 0 | 0
Round 2 | 8 | 0 | 0 | 0
Round 3 | 8 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Create / Proposal (ClubOrganizer)
EVT-CRT-01 | Tao de xuat su kien hop le | 1. Dang nhap ClubOrganizer 2. Mo Create Event 3. Nhap ten, mo ta, thoi gian, dia diem, cau hinh ve 4. Luu nhap | Tao su kien trang thai Draft/Pending, hien thi trong danh sach cua CLB | Login ClubOrganizer | Passed | 2026-06-04 | NhanKX | Passed | 2026-06-26 | NhanKX | Passed | 2026-06-26 | LinhNN
EVT-CRT-02 | Tao su kien trung khung gio dia diem | 1. Tao su kien tai dia diem/thoi gian da co su kien khac 2. Luu | He thong canh bao xung dot lich (Schedule Conflict), chan luu | Da co su kien tai khung gio do | Passed | 2026-06-08 | LinhNN | Passed | 2026-06-29 | LinhNN | Passed | 2026-06-29 | TuanDPH
EVT-CRT-03 | Submit de xuat len ICPDP | 1. Mo su kien Draft 2. Nhan Submit to ICPDP | Chuyen trang thai sang Pending Approval, gui thong bao ICPDP | Su kien o trang thai Draft | Passed | 2026-06-10 | TuanDPH | Passed | 2026-07-01 | TuanDPH | Passed | 2026-07-01 | NhanKX
Approve (ICPDP)
EVT-APR-01 | ICPDP phe duyet de xuat | 1. Dang nhap ICPDP 2. Mo de xuat Pending 3. Nhan Approve | Su kien chuyen Approved, gui thong bao cho CLB | Co de xuat Pending | Passed | 2026-06-12 | NhanKX | Passed | 2026-07-03 | NhanKX | Passed | 2026-07-03 | LinhNN
EVT-APR-02 | ICPDP tu choi kem ly do | 1. Mo de xuat Pending 2. Nhan Reject, nhap ly do | Su kien chuyen Rejected, hien thi ly do cho CLB | Co de xuat Pending | Passed | 2026-06-15 | LinhNN | Passed | 2026-07-06 | LinhNN | Passed | 2026-07-06 | TuanDPH
Publish (CTSV)
EVT-PUB-01 | CTSV publish su kien da duyet | 1. Dang nhap CTSV 2. Mo su kien Approved 3. Nhan Publish | Su kien hien thi cong khai tren trang chu cho toan bo sinh vien | Su kien Approved | Passed | 2026-06-17 | TuanDPH | Passed | 2026-07-08 | TuanDPH | Passed | 2026-07-08 | NhanKX
EVT-PUB-02 | Xem chi tiet su kien cong khai (Guest) | 1. Mo trang chu 2. Chon 1 su kien da Publish | Hien thi day du thong tin su kien, nut Dang ky/Mua ve | Su kien da Publish | Passed | 2026-06-19 | NhanKX | Passed | 2026-07-10 | NhanKX | Passed | 2026-07-10 | LinhNN
EVT-PUB-03 | Tim kiem & loc su kien | 1. Mo Events 2. Loc theo loai hinh (Workshop) va CLB | Tra ve danh sach dung dieu kien loc | Co du lieu su kien | Passed | 2026-06-02 | LinhNN | Passed | 2026-06-24 | LinhNN | Passed | 2026-06-24 | TuanDPH
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Registration & Ticketing
Feature | Registration & Ticketing | [13 empty] | Passed
Test requirement | Kiem thu dang ky/huy tham gia, mua ve va thanh toan online cua sinh vien. | [13 empty] | Failed
Number of TCs | 8 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 7 | 0 | 0 | 0
Round 2 | 7 | 0 | 0 | 0
Round 3 | 7 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Registration
REG-RGS-01 | Sinh vien dang ky su kien mien phi | 1. Dang nhap Student 2. Mo su kien con slot 3. Nhan Dang ky | Dang ky thanh cong, giam so slot, hien thi trong My Events | Su kien con slot | Passed | 2026-06-04 | TuanDPH | Passed | 2026-06-26 | TuanDPH | Passed | 2026-06-26 | NhanKX
REG-RGS-02 | Dang ky su kien da het slot | 1. Mo su kien het slot 2. Nhan Dang ky | Hien thi "Da het slot", chan dang ky | Su kien full | Passed | 2026-06-08 | NhanKX | Passed | 2026-06-29 | NhanKX | Passed | 2026-06-29 | LinhNN
REG-RGS-03 | Dang ky su kien trung lich ca nhan | 1. Dang ky su kien trung khung gio voi su kien da tham gia | He thong canh bao trung lich, chan/hoi xac nhan | Da co su kien cung khung gio | Passed | 2026-06-10 | LinhNN | Passed | 2026-07-01 | LinhNN | Passed | 2026-07-01 | TuanDPH
REG-RGS-04 | Huy dang ky su kien | 1. Mo My Events 2. Chon su kien 3. Nhan Huy dang ky | Huy thanh cong, hoan tra slot | Da dang ky su kien | Passed | 2026-06-12 | TuanDPH | Passed | 2026-07-03 | TuanDPH | Passed | 2026-07-03 | NhanKX
Ticketing & Payment
REG-PAY-01 | Mua ve su kien co phi thanh cong | 1. Mo su kien co phi 2. Chon loai ve, so luong 3. Thanh toan qua cong tich hop | Thanh toan thanh cong, cap ve dinh danh kem QR, gui email xac nhan | Login Student, con ve | Passed | 2026-06-15 | NhanKX | Passed | 2026-07-06 | NhanKX | Passed | 2026-07-06 | LinhNN
REG-PAY-02 | Thanh toan that bai / huy giao dich | 1. Mua ve 2. Huy tai cong thanh toan hoac the loi | Giao dich that bai, khong cap ve, khong tru slot | None | Passed | 2026-06-17 | LinhNN | Failed | 2026-07-08 | LinhNN | Failed | 2026-07-08 | TuanDPH
REG-PAY-03 | Xem lich su thanh toan | 1. Mo My Payments | Hien thi danh sach giao dich va trang thai | Da co giao dich | Passed | 2026-06-19 | TuanDPH | Passed | 2026-07-10 | TuanDPH | Passed | 2026-07-10 | NhanKX
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Check-in & QR
Feature | Check-in & QR | [13 empty] | Passed
Test requirement | Kiem thu tao ma QR diem danh, quet check-in tai su kien va thong ke ty le tham gia. | [13 empty] | Failed
Number of TCs | 6 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 5 | 0 | 0 | 0
Round 2 | 5 | 0 | 0 | 0
Round 3 | 5 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Create QR (ClubOrganizer)
CHK-QR-01 | Tao ma QR diem danh cho su kien | 1. Dang nhap ClubOrganizer 2. Mo su kien dang dien ra 3. Nhan Create QR | Sinh ma QR diem danh, hien thi de nguoi tham gia quet | Su kien Published, dang dien ra | Passed | 2026-06-02 | NhanKX | Passed | 2026-06-24 | NhanKX | Passed | 2026-06-24 | LinhNN
Check-in / Scan
CHK-SCN-01 | Nguoi tham gia quet QR check-in hop le | 1. Mo QR Scan 2. Quet ma QR cua su kien | Xac nhan check-in thanh cong, cap nhat trang thai tham gia | Da co ve/dang ky hop le | Passed | 2026-06-04 | LinhNN | Passed | 2026-06-26 | LinhNN | Passed | 2026-06-26 | TuanDPH
CHK-SCN-02 | Quet ma QR khong hop le / gia mao | 1. Quet ma QR sai hoac cua su kien khac | Tu choi check-in, hien thi loi ma khong hop le | None | Passed | 2026-06-08 | TuanDPH | Passed | 2026-06-29 | TuanDPH | Passed | 2026-06-29 | NhanKX
CHK-SCN-03 | Check-in trung (da diem danh) | 1. Quet lai QR cua nguoi da check-in | Bao "Da check-in truoc do", khong ghi trung | Da check-in truoc do | Passed | 2026-06-10 | NhanKX | Passed | 2026-07-01 | NhanKX | Passed | 2026-07-01 | LinhNN
CHK-SCN-04 | Xem dashboard ty le check-in | 1. Mo dashboard su kien | Hien thi so lieu dang ky va ty le check-in thuc te | Co du lieu check-in | Passed | 2026-06-12 | LinhNN | Passed | 2026-07-03 | LinhNN | Passed | 2026-07-03 | TuanDPH
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case